CHECKLIST FOR THE DISTRICT III DESIGN BUILD PUSH BUTTON CONTRACT

# Scope Development:

### A.	Request For Proposal (RFP):  This is the most important step of the whole process.  It may take months to develop the main language for the RFP / Scope package that would satisfy both State and Federal requirements and approval.  This effort demands hard work and strong coordination among many offices, such as, Traffic Operations, Construction, Contractual Services Unit, Design and Specification Office, Work Program, and so forth.

B.	Select Projects

1.	MEET NEPA TYPE I AND PROGRAMMATIC CATEGORICAL EXCLUSION CHECKLIST.

2.	No Right of Way (ROW) involvement.

3.	Does it meet Federal safety related issues?  If YES, then use Federal Safety Funds.  If No, then the project will be funded by State Funds.

*Notes:  Regardless if it is a state funded project or it is a Federally funded project, all projects will have “complete oversight” by the Federal Highway Administration.

# Execution:

### Specification package (by Specification Office).

The main scope (RFP) will be submitted to the Specification office for review and to develop the specification package.

### Contract Acquisition Schedule (by District Contracts)

- RFP / Scope / Spec package will be sent to District Contracts for Advertisement.  At the same time, the Work Program office will have to work on the procedure in Step #3.

- Encumber Advertised Funds.

- Proposal / RFP / Scope / Specs will be posted on the FTP Site.

- Proposal / RFP / Scope / Specs will be sent to District Legal, to Central Office Construction, and to FHWA for review.

- Resolve comments / responses from those above agencies.

- Post Advertisement to FDOT’s website with the deadline for the letters of interest.

- Receive letters of interest, and set-up long list meeting with the technical review committee and the short list meeting with the District Selection / Awards Committee.

- Post the short listed firms (teams) and the protest deadline.

- Protest deadline ends, mailing out Proposal / RFP / Scope / Specs Package.

- Set-up the Pre-proposal Conference.

- After the Pre-proposal Conference meeting, set-up the deadline for the technical questions.

- Meeting conducted to open the Technical Proposals.

- Each Technical Proposal is evaluated by the members of the Technical Review Committee.

- Technical Review Committee Meeting is held.

- Final Technical Proposal scores are presented to the District Contract Office.

- A meeting is held to open the Price Proposals that were received and the Technical Scores, which are utilized to calculate the Adjusted Scores.

- The required funds are encumbered.

- Meeting is conducted with the Selection / Awards Committee.

- The Intended Award is posted, and the protest period is announced.

- Once the protest period has ended, the Contract is mailed to the awarded firm.

- The awarded firm returns the signed contract to the District Contract Office.

- Then the Contract is executed.

- And the Notice to Proceed (NTP) is issued.

### 3. 	Contract Funding (by Work Program).  Please note that many procedures in this step are occurring concurrently with Step #2.

- Check for FHWA approval of this contracting method.

- Check for the available funds and determine if the project was in the TIP / STIP.

- Check for the Request for Authorization (RFA) for the scope, location, and dollar amount; and indicate if it is State Funding or Federal Funding.

- Verify the program amounts and seek Federal authorization.

- Verify the environmental documentation and determine if the project is in the TIP / STIP.

- Process the Federal Authorization request through Central Office to FHWA.

- Receive Approval / Rejection from FHWA.

- Send the approved documentation to Traffic Operations.  Then the Notice to Proceed (NTP) may be issued once funds are encumbered.

# Construction:

The District Construction Office will manage the construction procedures, which will follow the construction guidelines established by the FHWA.  Inspection and final review / acceptance will have to be approved by the FHWA for the federally funded tasks.