## Sheet1
FIGURE 2-1
Project Type Timeline Comparisons
| Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A | LAP
|  | Lap Certification* |  |  | LAP Agreement |  |  | Evaluation/Selecton of Firm/Design | [17 empty] | Letting/Select a Low Construction Bidder/Prepare for Construction | [8 empty] | Construction
B | Design/Bid/Build | bar: 1 to 30
|  | Evaluation/Select a Design Firm | [5 empty] | Design/Review Process | [11 empty] | Letting/Select a Low Construction Bidder/Prepare for Construction | [8 empty] | Construction
C | Class 1/District Let | bar: 1 to 30
|  | Evaluation/Select a Design Firm | [5 empty] | Prepare 60% Plans |  |  | 60% Review/Comments/Prepare Final Plans/Review Comments/Prepare Spec. Package | [8 empty] | Letting/Select a Low Construction Bidder/Prepare for Construction | [8 empty] | Construction
D | Push Button | bar: 1 to 18
|  | Evaluation/Select a Design Firm | [5 empty] | Task Work Order |  | Design/Review | [5 empty] | Hands off | Construction
to Construction
E | Design/Build Pushbutton | bar: 1 to 12
|  | **Evaluation/Select a Design Firm | [5 empty] | Prepare 60% Plans |  |  | Review/Comments/Prepare Final Plans/DB Firm Procurement of Equipment
Construction
*Notes: This process would happen only one time. Once the local agency obtains the Certification, this 3 month ime can be removed from the timeline projection.
**Notes: Subsequent Task Work Orders will not require Evaluation/Selection of a Design-Build Firm.