DBPB III WEEKLY PROGRESS MEETINg minutes #26

FM No. 254677-2-52-91 & 254677-1-52-32 / FED: 8886 617 A (FO) & N/A / Contract No.  E7J81

June 22, 2016 – 10:00 Am

| Original Contract Time: | 1095 | Days | Original Contract Amount: | $9,731,258.98 |
| --- | --- | --- | --- | --- |
| Weather Extensions: | 0 | Days | Supplemental Agreements: | -$42,684.95 |
| Other Time Extensions: | 0 | Days | Present Contract Amount: | $9,688,574.03 |
| Updated Contract Time: | 1095 | Days |  |  |
|  |  |  | Amount Earned to Date:* | $4,714,980.31 $ 8360139.48268.06 |
| Current Contract Day:* | 332 54 |  | Percent Complete ($): | 45% |
| Days Remaining in Contract: | 763 |  | *As of the estimate | May 15, 2016 |
| Percent Complete (days): | 30 | % | Rev. Completion Date: | 7/25/2018 |

Cone & Graham: Tasks in Construction Update:

Task 4 – Signal Rebuild at SR 597 (Dale Mabry Hwy) @ Mapledale Blvd

Released for Construction 1/7/16. Task time expires 6/26/16.

Punch list thermo & crosswalk this week. Final as-builts next week then final inspection 7/7

Task 7 – Signal Rebuild US 301 and MLK

Released for construction 2/2/2016. Task time expires 7/8/16.

Next week pulling cable. After 7/5 punch list and clean up

Task 8 - Signal Rebuild US 41 at Big Bend Road

Released for construction 4/6/2016. Task time expires 8/15/2016.

6/23 last drill shaft then boring 6/27 then conduit

Task 10 – ITS ‐ Installation of Fiber along I‐75 from Big Bend Road to Gibsonton Dr.

Released for Construction 2/12/16. Task time expires 9/13/16.

Conduit across bridge this week, Install interduct/boxes/aprons. Then 7/11 pulling fiber

Task 13 – US 41 at Palm Avenue

Released for Construction 3/8/19. Task time expires 8/13/16.

This week relocate utilities, drill shaft next week. Drill shafts 6/27, signal boxes 7/5, conduit/boxes 7/11

Task 15 – MLK and 301 additional NB and SB left turn lanes

Released for Construction 1/7/16. Task time expires 6/30/16.

Thermo final striping done, final inspection needed 6/29.

Task 16 - Signal Installation, SR 688 / Ulmerton Road at Wilcox Road / 130th Avenue North

Released for construction 6/8/16. Task time expires 8/9/16.

Materials procurement, drill shaft 7/11

Task 20 – Milling & Resurfacing NB I-75 On-Ramp at Gibsonton Drive

NTP 5/9/16                       (Construction Only)

Structures have been delivered. Will be laying down temp striping 7/10. Pavement cure to start 7/10.

FDOT Project Concerns or Issues related to Safety, Maintenance of Traffic, Reported Accidents, Work Schedule, Erosion Control, Weather, and Lane Closure/Detour Notifications, Shop Drawings

Open Claims:

Task 8 – Time Extension Request

Task 16 – Time Extension Request

Task 17 – Time Extension Request

Task 18 – Time Extension Request

SA Status and Discussion:

Supplemental agreement in process for adding numerous pay items

Supplemental agreement in process for issues on initial tasks – all issues resolved, SA submitted to District Construction, and includes a 10 day time extension For Task 7.

|  | Action Items – Description | Due Date | Status |
| --- | --- | --- | --- |
| FDOT | Review Time extension for Task 8, 16, 17 & 18 | asap |  |

|  | New Pay Item Unit Prices Requested | Due Date | Status |
| --- | --- | --- | --- |

Open Discussion:

Next meeting Wednesday, June 29, 2016 at 10:00 a.m.