DBPB III WEEKLY PROGRESS MEETINg AGENDA #39

FM No. 254677-2-52-91 & 254677-1-52-32 / FED: 8886 617 A (FO) & N/A / Contract No.  E7J81

September 28, 2016 – 10:00 Am

| Original Contract Time: | 1095 | Days | Original Contract Amount: | $9,731,258.98 |
| --- | --- | --- | --- | --- |
| Weather Extensions: | 0 | Days | Supplemental Agreements: | -$545,329.73 |
| Other Time Extensions: | 0 | Days | Present Contract Amount: | $9,185,929.25 |
| Updated Contract Time: | 1095 | Days | Estimated Tasks Value: | $12,995,431.29 $12,9$1289,045.89 |
|  |  |  | Amount Earned to Date:* | $7,637,535.99 $ 8360139.48268.06 |
| Current Contract Day | 430 54 |  | Percent Complete ($): | 59% |
| Days Remaining in Contract: | 665 |  | *As of the estimate | September 18, 2016 |
| Percent Complete (days): | 39 | % | Rev. Completion Date: | 7/25/2018 |

Cone & Graham: Tasks in Construction Update:

Task 10 – ITS ‐ Installation of Fiber along I‐75 from Big Bend Road to Gibsonton Dr.

Released for Construction 2/12/16. Task time expires 9/22/16.

Completed, waiting for review of final test reports.

Task 16 - Signal Installation, SR 688 / Ulmerton Road at Wilcox Road / 130th Avenue North

Released for construction 6/8/16. Task time expires 11/6/16.

Installed mast arms on 9/26/16. Working on conductors/terminations this week followed by sidewalk and clean up next week 10/3/16 Requesting power for new service. As-builts will be prepared 10/12/16 signal inspection is tentatively set for 10/18/16.

Task 19 - US 19 at Bartelt Road & Buena Vista Lane

Released for construction 8/15/2016. Time expires 11/3/2016

Should be completed this week after themo issue is resolved. After that, final inspection will be requested.

Task 21 - Curlew at Gull Aire Pinellas - Mast arm foundation

Released for construction 9/9/16. Task time expires 2/25/17

On schedule. PCMs went in Monday 9/26/16 work zone signs will be going up 9/30/16 followed by temp signalization along with bores starting at night on 10/3/16. October 10th, at approximately 8:00 a.m., the existing foundation will be investigated, which involves removing the existing mast arm. followed by drill shafts on 10/12/16.

Task 22 – Ben T. Davis

Released for construction 9/15/16. Task time expires 3/4/17

Still in procurement phase. Work should begin Monday, October 3rd, with PCMs being installed then signs going in on the 7th and construction starting on the 10th installing erosion control and lighting conduit then lighting relocation on 10/20/16.

Task 24 - Arterial Signing and Marking

Released for construction 8/18/16. Time expires 2/22/2017

Submit detours for approval in an email a minimum of three weeks prior to detour date so that we can get required District Secretary approval. Procurement issues with Chevron signs. Will be at some locations twice. Will be doing three weeks of day work.

Task 25 – Port of Tampa ITS

NTP 6/20/16 (Construction Only) Task time expires 2/15/17

Continuing with conduit, pull boxes, and then moving to interdict on 10/10/16

Task 29 – Signal Installation, SR 54 at River Glen Blvd.

NTP 6/30/16 (Construction Only) Task time expires 2/5/2017

Construction will start next week10/4/16. VMS board going in today 9/28/16. Post mount signs next week. The contractor will build the power service as well as erosion control starting 10/5/16, then continue with signal work.

FDOT Project Concerns or Issues related to Safety, Maintenance of Traffic, Reported Accidents, Work Schedule, Erosion Control, Weather, and Lane Closure/Detour Notifications, Shop Drawings

Failing Thermoplastic on Task 19.

Open Claims:

Task 17 – 6/2/16 Time Extension Request - Delay to CA

Task 17 – 6/15/16 Time Extension Request - Delay to Prepare 60% Plans

Task 17 – 9/19/16 Request for Equitable Adjustment

Task 18 – 6/2/16 Time Extension Request - Delay to CA

Task 18 – 6/15/16 Time Extension Request - Delay to Prepare 60% Plans

Task 26 – 9/2/16 Time Extension Request – Traffic Design concerns

Task 27 – 9/16/16 Time Extension Request – Inaccurate Survey Information

SA Status and Discussion:

Supplemental Agreement 05 in process for adding numerous pay items – At district office for review

Supplemental Agreement 06 in process for signal hanger credits on initial tasks – At district office for review

Supplemental Agreement 07 in process for adding numerous pay items – Waiting for info from Louis

Supplemental Agreement 08 in process for TECO relocation – Will process once work is complete

See action items page

Open Discussion:

CPM Schedule: Recommend removing completed Tasks, adding task numbers next to NTP, add all tasks that have an NTP issued.

Next meeting Wednesday, October 5, 2016 at 10:00 a.m.