FDOT District 7 DBPB III Contract – Pros & Cons

Pros

- This Design-Build Push Button (DBPB) Contract is an effective way to resolve safety issues quickly with reduced procurement, design and construction times along with reduced design costs. For example, procurement time is reduced because each Task Work Order does not require a separate contract.

- The DBPB Contract is a better means to address Traffic Operation concerns compared with the traditional Design-Bid-Build Project.  The focus on traffic operations allows for the isolation of a single design element, which is not possible with RRR projects.

- DBPB contract utilized multiple design/construction teams, which consequently created many jobs with hiring additional people as well as saved jobs in other offices around Florida by sharing work.

- Regardless of how large the task is, the schedule cannot be more than 330 days with a Constructability Analysis.

- Contractor has to ability to have direct input in the design process.

- There were 31 safety tasks issued, which addressed a wide variety of safety projects ranging from high emphasis crosswalks to signal rebuilds / installations.

- In the design process, the FDOT District Design Engineer allowed for a short review time of the plans.  In a normal contract, the review time is four weeks compared to two weeks for this DBPB Contract.

- Design and Construction Offices worked together to resolve issues much more quickly than the traditional process.

- There are lower design fees with the DBPB Contract.  For traditional projects, the design fee is almost 30% whereas the design fee for the DBPB Contract is 20% of the construction fee plus an additional 2% of the construction fee when a Constructability Analysis is required.

- The use of as-built construction plans has contributed to a decreased design time.

- The contract is lump sum, so not every item needs to be tracked.

- Other Districts throughout the state are pursuing the DBPB Contract using Federal Funds based on the same model as District 7.

- The quantities from the current DBPB contract can be used as a template for the next DBPB contract.

- Striping jobs can be finished quickly.

Cons

- FDOT has a significant workload and cannot primarily focus on the DBPB contract at all times.  For example, the FDOT has limited staff available to review multiple tasks concurrently.

- Local Maintaining Agencies are to be held to the same review period as internal FDOT reviewers.  Delays associated with the submittal of review comments from FDOT staff and the maintaining agencies results in the DBPB Team filing a delay claim, requesting days.

- Design Build unit prices are usually higher than the statewide average unit prices.

- The inclusion of additional pay items with this DBPB contract versus the traditional Design-Bid-Build Contract is more difficult, which limits the types of projects that can be addressed under this contract.

- Constructability Assessment needs to provide an accurate assessment of the existing conditions of the project site including:  right-of-way, utilities and existing roadway features.  Designer should seek constructability feedback from the contractor. This is difficult to accomplish in 30 days and FDOT is expecting exploratory work to be completed prior to design resulting in re-work that is not compensated for. DBPB Team is regularly required to develop and present a design that was constructible within the constraints of the contract and to meet standard requirements. Additional investigation and review is needed during the concept development phase.

- FDOT needs to implement a better procedure / process to stagger the release of new tasks. Many tasks were released at the end of the fiscal year.

- Before the NTP was issued, the DBPB team offered complimentary reviews of the scope and fee resulting in many revisions. More reviews during the scope and concept development process is needed.

- Additional clarification of the conceptual design is required to identify the need for a Design Variation / Exception earlier in the design process. Per Florida Design Manual, variations/exceptions should be identified and approved during the concept development phase.