## Sheet1
Average
| Project Budget | Construction | Construction | % Difference |  | % Difference
Task | Include Construction, | Cost - Statewide | Cost - DBPB | vs. Statewide |  | vs. Statewide
No. | CEI & Design ($) | Unit Price* | Unit Price** | Unit Price |  | Unit Price
TABLE 8-2: Summary of Average % Difference in Construction Costs for DBPB III vs. Statewide Unit Prices
Average % Difference
[5 empty] | Corresponding | in Construction Costs
[5 empty] | Task | DBPB III Unit Price vs.
Project Type Description |  |  |  |  | Numbers | Statewide Unit Price
Installation of Turn Lanes/Modifications to Turn Lanes |  |  |  |  | #5, #6, #11, #15, #22, #23, #35, #43, #45 | 75.37%
5 | 446011.51 | 145603.73 | 309730.22 | 112.7%
6 | 120941.36 | 49283.44 | 83987.06 | 70.42%
11 | 853742.44 | 646977 | 592876.7 | -8.362%
15 | 961427.77 | 334180.28 | 656712.96 | 96.51%
22 | 884727.75 | 299530.43 | 622280.79 | 107.8%
23 | 269599.31 | 93276.92 | 190629.71 | 104.4%
35 | 382401.13 | 185887.57 | 270125.48 | 45.32%
43 | 622239.59 | 250129.85 | 441307.13 | 76.43%
45 | 470373.99 | 190475.13 | 329805.13 | 73.15%
Miscellaneous Signing & Pavement Markings |  |  |  |  | #3, #24, #44 | 3.668%
3 | 88732.34 | 50802.86 | 63744.5 | 25.47%
24 | 801864.46 | 767933.87 | 572760.33 | -25.42%
44 | 416099.2 | 263974.42 | 292868.02 | 10.95%
New Signal/Signal Rebuild/Signal Replacement |  |  |  |  | #4, #7, #8, #13, #16, #21, #40, #46 | 29.51%
4 | 545690.22 | 317540.9 | 375758.35 | 18.33%
7 | 559717.8 | 336303.49 | 382320.9 | 13.68%
8 | 712062.97 | 418339.23 | 488868.15 | 16.86%
13 | 507850.83 | 292983.61 | 348668.6 | 19.01%
16 | 433794.68 | 242669.7 | 304359.89 | 25.42%
21 | 233339.96 | 95868.29 | 164152.75 | 71.23%
40 | 654436.17 | 353665.43 | 462088.72 | 30.66%
46 | 832376.34 | 418300.67 | 589388.92 | 40.9%
Replace/Install Street Lighting |  |  |  |  | #17, #18, #31 | 33.21%
17 | 835114.75 | 467364.25 | 587117.54 | 25.62%
18 | 946605.08 | 429013.88 | 666623.14 | 55.38%
31 | 251562.43 | 149198.2 | 176999.8 | 18.63%
Median Modifications |  |  |  |  | #19, #32, #41 | 65.94%
19 | 102709.33 | 37839.93 | 71848.97 | 89.88%
32 | 66104.58 | 28636.72 | 45927.13 | 60.38%
41 | 919673.25 | 440720.55 | 650327.5 | 47.56%
Installation of Midblock Crossings or Midblock Features |  |  |  |  | #26, #36, #47, #48 | 28.98%
26 | 384974.18 | 251062.68 | 269893.96 | 7.501%
36 | N/A | N/A | N/A | N/A
47 | 212149.61 | 137920.86 | 149291.38 | 8.244%
48 | 90247.1 | 36857.4 | 63103.4 | 71.21%
Bicycle Lanes Safety Improvements |  | 292024.9 | 607884.13 | 108.2% | #33 | 108.2%
Miscellaneous Sign Structures |  | 57700.11 | 57287.55 | -0.715% | #12 | -0.715%
Installation of Intelligent Transportation System (ITS) Features |  | 406054.19 | 478482.3 | 17.84% | #10 | 17.84%
Milling & Resurfacing |  | 231126.58 | 419105.68 | 81.33% | #27 | 81.33%
Skid Resistance Improvements |  | 209901.16 | 320027.14 | 52.47% | #2 | 52.47%
Relocation of Crosswalks |  | 108000.04 | 150150.58 | 39.03% | #28 | 39.03%
Installation of On-Ramp |  | 303666.18 | 503807.6 | 65.91% | #30 | 65.91%
Installation of Guardrail |  | 554066.11 | 502072.5 | -9.384% | #37 | -9.384%